## Sheet1
ID | Fellowship Year | Month | Phase | Workstream | Deliverable | Definition of Done | Due Date | Commitment Tier | Priority | Status | Progress % | Estimated Hours | Dependency / Trigger | Evidence / Link | Notes / Revision | Health
M009 | Year 1 | 2026-08-01 | Foundation | Second Mind | Build chunking, metadata, embedding, and indexing | New journal entries can be chunked and indexed locally with dates and source metadata preserved. | 2026-08-31 | Core | High | Complete | 100% | 12 | Journal ingestion is working reliably. | 2026-08-21 • commit 4e512f2 • 38 tests passed • sample index/query verified • unchanged re-index skipped 3/3. | Codex reconciliation: definition of done verified with synthetic journals only; no private content inspected. Next: approve AGENTS.md transition to M013. | Complete
M013 | Year 1 | 2026-09-01 | First Outputs | Second Mind | Deliver natural-language retrieval with citations | A user can ask a question and receive relevant passages with source entry and date citations. | 2026-09-30 | Core | High | Complete | 100% | 14 | Indexing pipeline is stable. | 2026-08-21 • 47 tests passed • cited library retrieval and insufficient-evidence refusal verified • branch codex/m013-natural-language-retrieval | Codex reconciliation: M013 verified with synthetic journals only; no private content inspected. Next: approve transition to M018 and provide five private questions for local-only scoring. | Complete
M018 | Year 1 | 2026-10-01 | First Outputs | Second Mind | Pass the five-question retrieval test | Five real journal questions are scored for retrieval quality, citation accuracy, and appropriate refusal. | 2026-10-31 | Core | High | Planned | 0% | 8 | Natural-language retrieval is implemented. |  |  | Due Soon
M021 | Year 1 | 2026-11-01 | First Outputs | Second Mind | Stabilize MVP v0.1 | The MVP runs locally, includes insufficient-evidence refusal behavior, has a README, and is useful in repeated use. | 2026-11-30 | Core | High | Planned | 0% | 10 | Five-question test findings are available. |  |  | Future
M026 | Year 1 | 2026-12-01 | Consolidate | Second Mind | Automate updates and document backups | New entries can be added through a repeatable command or workflow, and the data/index backup process is tested. | 2026-12-31 | Core | High | Planned | 0% | 8 | MVP v0.1 is stable. |  |  | Future
M030 | Year 1 | 2027-01-01 | Method Formation | Second Mind | Log usage and identify the top failure modes | At least ten real uses are logged and the top three failure patterns are prioritized. | 2027-01-31 | Core | High | Planned | 0% | 5 | MVP is usable enough for repeated use. |  |  | Future
M035 | Year 1 | 2027-02-01 | Method Formation | Second Mind | Ship v0.2 fixes | The top retrieval or usability failures from the usage log are fixed and retested. | 2027-02-28 | Support | High | Planned | 0% | 8 | Failure-mode priorities are clear. |  |  | Future
M047 | Year 1 | 2027-05-01 | Validate Direction | Second Mind | Make the local-hardware decision gate | Decide whether current hardware is sufficient or a Mac mini is justified by actual usage and deployment needs. | 2027-05-31 | Support | Medium | Planned | 0% | 3 | Reassess current products and pricing at the time. |  |  | Future
M051 | Year 2 | 2027-06-01 | Systematize | Second Mind | Document architecture v1 and the media roadmap | Current components, data flows, maintenance steps, scaling risks, and BeReal/media sequencing are documented. | 2027-06-30 | Support | High | Planned | 0% | 7 | Journal MVP is stable and in real use. |  |  | Future
M054 | Year 2 | 2027-07-01 | Systematize | Second Mind | Prototype dated-media metadata ingestion | A small BeReal or photo sample maps files to dates and links them to journal-entry metadata without full search yet. | 2027-07-31 | Core | Medium | Planned | 0% | 10 | Only proceed if the journal MVP is used regularly. |  |  | Future
M059 | Year 2 | 2027-08-01 | Soft Launch | Second Mind | Run a backup-and-restore test | The journal data, index, configuration, and metadata can be restored from a clean backup. | 2027-08-31 | Support | High | Planned | 0% | 5 | Architecture and backup instructions exist. |  |  | Future
M067 | Year 2 | 2027-10-01 | Operationalize | Second Mind | Create the local deployment plan and budget | Document required hardware, software, security, migration steps, cost, and why the setup is justified. | 2027-10-31 | Support | Medium | Planned | 0% | 5 | Use current hardware information and actual usage. |  |  | Future
M072 | Year 2 | 2027-11-01 | Operationalize | Second Mind | Complete a privacy and security review | Threats, sensitive-data boundaries, local access controls, backup exposure, and deletion procedures are reviewed. | 2027-11-30 | Support | High | Planned | 0% | 5 | Deployment plan exists. |  |  | Future
M076 | Year 2 | 2027-12-01 | Consolidate | Second Mind | Generate a year-in-review query report | Use the system to answer a defined set of year-review questions and assess whether it improves reflection. | 2027-12-31 | Support | High | Planned | 0% | 4 | System has a full year of usable data. |  |  | Future
M084 | Year 2 | 2028-02-01 | Application | Second Mind | Run the deployment rehearsal | A clean setup can be reproduced from documentation on the chosen local hardware or current machine. | 2028-02-29 | Support | High | Planned | 0% | 7 | Deployment plan and security review are complete. |  |  | Future
M086 | Year 2 | 2028-03-01 | Transition | Second Mind | Release stable local v1 | The system runs locally, updates reliably, cites sources, refuses weak answers, and has backup/restore documentation. | 2028-03-31 | Core | High | Planned | 0% | 10 | Deployment rehearsal passes. |  |  | Future
Future
Future
Future

## Codex Execution
ID | Milestone | Month | Work Type | Codex Readiness | Roadmap Status | Agent Status | Human Gate / Required Input | Last Verified | Verification Evidence | Next Action
M009 | Build chunking, metadata, embedding, and indexing | 2026-08-01 | Engineering | Complete | Complete | Verified | M013 transition approved and completed. | 2026-08-21 | 38 tests passed; synthetic index created 3 chunks; query returned date/source/title/chunk; unchanged re-index skipped 3/3; commit 4e512f2. | Completed; retained as M013 prerequisite evidence.
M013 | Deliver natural-language retrieval with citations | 2026-09-01 | Engineering | Complete | Complete | Verified | Approve transition to M018 and provide five private questions for local-only scoring; do not place private content in this workbook. | 2026-08-21 | 47 tests passed; natural-language CLI returned only the cited library passage; unrelated hash-collision candidates were filtered; a zero-evidence query returned no passage. | Prepare a privacy-safe offline five-question retrieval scoring harness after approval.
M018 | Pass the five-question retrieval test | 2026-10-01 | Evaluation + human evidence | Blocked | Planned | Awaiting Input | Provide five private questions and score results locally; do not place private content in this workbook. |  |  | Provide five private questions locally; then run the privacy-safe offline scoring harness.
M021 | Stabilize MVP v0.1 | 2026-11-01 | Engineering + adoption | Blocked | Planned | Not Started | Confirm repeated-use usefulness after the five-question findings. |  |  | Use M018 findings to define stabilization work.
M026 | Automate updates and document backups | 2026-12-01 | Engineering + operations | Blocked | Planned | Not Started | Approve backup location and recovery expectations. |  |  | Wait for stable MVP v0.1; then design a repeatable update and backup workflow.
M030 | Log usage and identify the top failure modes | 2027-01-01 | Human evidence | Time-gated | Planned | Not Started | Complete at least ten real uses and record only non-sensitive failure categories. |  |  | Collect real usage before prioritizing failure modes.
M035 | Ship v0.2 fixes | 2027-02-01 | Engineering | Blocked | Planned | Not Started | Approve the failure-mode priorities before fixes. |  |  | Implement and retest only the prioritized failures.
M047 | Make the local-hardware decision gate | 2027-05-01 | Decision | Time-gated | Planned | Not Started | Review actual usage and current hardware/pricing at the decision date. |  |  | Reassess at the scheduled gate using current evidence.
M051 | Document architecture v1 and the media roadmap | 2027-06-01 | Documentation | Blocked | Planned | Not Started | Confirm the journal MVP is stable and regularly used. |  |  | Document architecture and sequence the media roadmap.
M054 | Prototype dated-media metadata ingestion | 2027-07-01 | Engineering + private media | Time-gated | Planned | Not Started | Confirm regular use and select a privacy-safe media sample/procedure. |  |  | Proceed only after the regular-use gate is satisfied.
M059 | Run a backup-and-restore test | 2027-08-01 | Operations | Blocked | Planned | Not Started | Approve a recoverable backup-and-restore rehearsal. |  |  | Run a clean, recoverable restore test after documentation exists.
M067 | Create the local deployment plan and budget | 2027-10-01 | Decision + documentation | Time-gated | Planned | Not Started | Supply current hardware constraints and budget preferences. |  |  | Prepare the plan with current usage and hardware facts.
M072 | Complete a privacy and security review | 2027-11-01 | Security review | Blocked | Planned | Not Started | Review threats, access controls, backup exposure, and deletion choices. |  |  | Review security after the deployment plan exists.
M076 | Generate a year-in-review query report | 2027-12-01 | Human evidence | Time-gated | Planned | Not Started | Run the defined year-review questions locally after a full year of usable data. |  |  | Wait for a full year of usable data.
M084 | Run the deployment rehearsal | 2028-02-01 | Operations | Blocked | Planned | Not Started | Approve the target machine and clean-rehearsal conditions. |  |  | Rehearse only after deployment and security gates pass.
M086 | Release stable local v1 | 2028-03-01 | Release | Blocked | Planned | Not Started | Approve release after rehearsal and final acceptance review. |  |  | Release only after the rehearsal passes.

## Update Log
Updated At | Milestone ID | Field | Before | After | Evidence / Reason | Updated By
2026-08-21 | WORKBOOK | Maintenance setup | Single roadmap sheet | Added Codex Execution and Update Log | User requested a maintained project copy. | Codex
2026-08-21 | M009 | Status | In Progress | Complete | Definition of done verified against code, tests, and synthetic CLI checks. | Codex
2026-08-21 | M009 | Progress % | 0% | 100% | All August acceptance behavior verified. | Codex
2026-08-21 | M009 | Evidence / Link | Blank | Verification recorded | 38 tests; index/query metadata; unchanged re-index 3/3 skipped; commit 4e512f2. | Codex
2026-08-21 | M009 | Notes / Revision | Blank | Reconciliation note recorded | Synthetic samples only; no private journal content inspected. | Codex
2026-08-21 | M013 | Status | Planned | Complete | Definition of done verified against code, tests, and synthetic CLI checks. | Codex
2026-08-21 | M013 | Progress % | 0% | 100% | All cited retrieval and insufficient-evidence behavior verified. | Codex
2026-08-21 | M013 | Evidence / Link | Blank | Verification recorded | 47 tests; cited library retrieval; collision candidates filtered; zero-evidence query refused. | Codex
2026-08-21 | M013 | Notes / Revision | Blank | Reconciliation note recorded | Synthetic samples only; no private journal content inspected. | Codex